## Product Backlog
Project | dealmart.com | Column3 | Column4 | Column5 | Column6
Stakeholders/customers/users | mr. x
Created by | name of the product owner
Epic | User story ID | Feature/Title of Story | User Story | Status | Acceptance Criteria
For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website. DealMartEpic_001 | US001 | First time visitor can make the payment as a guest user without having to register. | As a first-time visitor to the website: I want to be able to buy listed products, so that I can use the product I buy. | New
| US002 | New user can register in the website | As a first-time visitor to the website: I want to be able to register on the website, so that I can browse and buy the listed products on the website. | New
| US003 | Registered users can browse items listed | As a registered user of the website: I want to be able to browse listed products from the website, so that I can make my choice and buy a listed product from the website. | New
| US004 | Registered users can add items to the cart | As a registered user of the website: I want to be able to add items to the cart, so that I can buy a listed product from the website. | New
| US005 | Registered users can make payment for the items added to the cart | As a registered user of the website: I want to be able to buy listed products, so that I can use the product I buy. | New

## Sprint Planning
Project | dealmart.com | Column3 | Column4 | Column5 | Column6
Scrum Team | Dev, QA, PO, scrum master, DecOps etc.
Created by | name of the product owner
Epic | User story ID | Feature/Title of Story | User Story | Story points | Sprints
For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register. | As a first-time visitor to the website: I want to be able to buy listed products, so that I can use the product I buy. | 8 | 1
| US002 | New user can register in the website | As a first-time visitor to the website: I want to be able to register on the website, so that I can browse and buy the listed products on the website. | 3 | 1
| US003 | Registered users can browse items listed | As a registered user of the website: I want to be able to browse listed products from the website, so that I can make my choice and buy a listed product from the website. | 5 | 2
| US004 | Registered users can add items to the cart | As a registered user of the website: I want to be able to add items to the cart, so that I can buy a listed product from the website. | 5 | 3
| US005 | Registered users can make payment for the items added to the cart | As a registered user of the website: I want to be able to buy listed products, so that I can use the product I buy. | 8 | 3

## Tasks
QA Tasks | Dev Tasks
Reviewing user stories | Reviewing user stories
Creating test cases | Setting up dev environment
Reviewing test cases | Developing programs
Setting up test environment | Code review
Creating test data | Creating unit test cases
Executing manual test | Executing unit tests
Automation setup | Merging code
Automation design | Creating builds
Automating test cases | Fixing bugs
Re-testing bugs
Regression testing
Demo user testing